## Sheet1
Task | Story | Priority | Status | Assinged to Sprint
Planning and Research | Define project goals and objectives | High | Completed | Sprint 1
Planning and Research | Conduct user research and define target audience | High | Completed | Sprint 1
Planning and Research | Research existing recycling and gamification apps | High | Completed | Sprint 1
Planning and Research | Develop initial app concept user flow diagrams | High | Completed | Sprint 1
App UI Design and Prototyping | Create wireframes and mockups for key screens | High | Completed | Sprint 1
App UI Design and Prototyping | Finalize app UI design and color palette | High | Completed | Sprint 1
App UI Design and Prototyping | Design app icons and additional visual elements | Medium | Completed | Sprint 2
App UI Design and Prototyping | Develop interactive prototype using a prototyping tool | High | Completed | Sprint 2
Backend Development | Set up development environment and install dependencies | Medium | Completed | Sprint 2
Backend Development | Develop API for user authentication, data storage, and leaderboard | High | Completed | Sprint 2
Backend Development | Implement core functionalities like material processing and point system | High | Completed | Sprint 3
Frontend Development | Integrate UI components and connect them to backend API | High | Completed | Sprint 3
Frontend Development | Implement gamification elements like avatars, customization, and rewards | High | Completed | Sprint 3
Frontend Development | Develop features for social interaction and leaderboards | High | Completed | Sprint 3
Testing and Debugging | Perform unit and integration testing for each component | Medium | In progress | Sprint 4
Testing and Debugging | Conduct user testing to identify usability issues and improve app flow | High | In progress | Sprint 4
Testing and Debugging | Fix bugs and refine the app based on user feedback | High | In progress | Sprint 4
Deployment and Launch | Prepare app for deployment for a group of users | Medium | In progress | Sprint 5
Deployment and Launch | Share app with the small group | Medium | Not Started | Sprint 5
Deployment and Launch | Test the app while users are active | High | Not Started | Sprint 5
Post-Launch Maintenance and Updates | Monitor app usage and performance | Medium | Not Started | Sprint 6
Post-Launch Maintenance and Updates | Address any reported bugs and issues | High | Not Started | Sprint 6
Post-Launch Maintenance and Updates | Develop new features and enhancements based on user feedback | High | Not Started | Sprint 6